## 1.1 Charter
Office of the Inspector General and Director of Compliance (OIGC)
July 1, 2008 – June 30, 2009
DETAILED WORK PLAN
PRIMARY ACTIVITY | LEGAL AUTHORITY | ACTIONS TAKEN OR PLANNED | STAFF | STATUS | COMPLETION DATE | DELIVERABLE | ACTIONS ITEMS/PLAN PROCESS | PLAN IMPLEMENTATION PROCESS | ESTIMATED HOURS
1.0 Establishment of OIGC
1.1 Develop BOG Audit & Compliance Committee Charter
| BOG F.S. 20.055 & 20.155 | Action Taken: • Draft Charter reviewed by Audit Committee and SUAC members. Planned: • Meeting with key constituencies; i.e., UBOT Audit Committee Chairs, individual Chief Audit Executives | Harper/Clark | Pending | Final Draft for Committee's Notice: January 29, 2009 Final Draft for Committee's Approval: March 25-26, 2009 | Audit Compliance Committee Charter approved by BOG | • Send draft to Audit Committee Chair, Vice Chair, BOG Chair, and Chancellor for input. [Done October '08] • Incorporate input from key constituents above, and then vet new draft with university CAEs (SUAC). [Awaiting Univ. input by 12/8/08] • Prepare for Audit & Compliance Committee notice (January 09) and approval (March 09). • Once draft is finalized, post on BOG IG Web pages. | • Meet with key constituencies -identify individuals and groups -send request for information [Done 11/14/08. Awaiting input by 12/8/08] -develop agenda for SUAC meetings [Done. Derry met with SUAC 11/19/08.] | 100

## 1.2 Compliance
Office of the Inspector General and Director of Compliance (OIGC)
July 1, 2008 – June 30, 2009
DETAILED WORK PLAN
PRIMARY ACTIVITY | LEGAL AUTHORITY | ACTIONS TAKEN OR PLANNED | STAFF | STATUS | COMPLETION DATE | DELIVERABLE | ACTIONS ITEMS/PLAN PROCESS | PLAN IMPLEMENTATION PROCESS | ESTIMATED HOURS
1.0 Establishment of OIGC
1.2 Develop Compliance Program Plan
| BOG F.S. 20.055 & 20.155 | Action Taken: • Reviewed professional and SUS compliance structures. Planned: • Creation of compliance structure to be published. • Training sessions will be delivered to strengthen procedures and compliance. | Harper/Clark | Pending | February, 2009 | Published compliance structure and training materials. | • Create compliance structure for OIGC. • Vet compliance structure with key constituents. • Once approved, post to BOG IG Web pages and include in BOG How To Manual. • Select topics as appropriate for professional development training sessions for BOG staff. | • Compliance structure will be drafted in Word to keep in a notebook for OIGC use and will be included in BOG How To Manual. | 200

## 1.3 OIGC Pol & Proc
Office of the Inspector General and Director of Compliance (OIGC)
July 1, 2008 – June 30, 2009
DETAILED WORK PLAN
PRIMARY ACTIVITY | LEGAL AUTHORITY | ACTIONS TAKEN OR PLANNED | STAFF | STATUS | COMPLETION DATE | DELIVERABLE | ACTIONS ITEMS/PLAN PROCESS | PLAN IMPLEMENTATION PROCESS | ESTIMATED HOURS
1.0 Establishment of OIGC
1.3 Develop OIGC Policies & Procedures
|  | Action Taken: Identified and obtained • list of state agency IG's policies and procedures, • Professional Association Standards including Peer Review Process, • met with appropriate BOG staff to discuss needs and current procedures for tracking and handling consumer complaints and investigation requests. Planned: Draft Audit/Investigative procedures for OIGC and obtain input from SUS member institutions, • Establish policies and procedures for OIGC unit and BOG How to Manual. | Harper/Clark | Pending |  | • Transition document in preparation for new Chancellor • OIGC Policies & Procedures Manual • Abbreviated Policies & Procedures for BOG Web site • OIGC Policies & Procedures for BOG How To Manual • Preparation for BOG Lunch and Learn Series, "What We Do"

## 1.4 Univ Audits
Office of the Inspector General and Director of Compliance (OIGC)
July 1, 2008 – June 30, 2009
DETAILED WORK PLAN
PRIMARY ACTIVITY | LEGAL AUTHORITY | ACTIONS TAKEN OR PLANNED | STAFF | STATUS | COMPLETION DATE | DELIVERABLE | ACTIONS ITEMS/PLAN PROCESS | PLAN IMPLEMENTATION PROCESS | ESTIMATED HOURS
1.0 Establishment of OIGC
1.4 Develop Procedures for Monitoring University Audit Activities
|  | Action Taken: Identified and obtained • list of state agency IG's policies and procedures, • Professional Association Standards including Peer Review Process, • met with appropriate BOG staff to discuss needs and current procedures for tracking and handling consumer complaints and investigation requests. Planned: Draft Audit/Investigative procedures for OIGC and obtain input from SUS member institutions, • Establish policies and procedures for OIGC unit and BOG How to Manual. | Harper/Clark | Pending |  | • Transition document in preparation for new Chancellor • OIGC Policies & Procedures Manual • Abbreviated Policies & Procedures for BOG Web site • OIGC Policies & Procedures for BOG How To Manual • Preparation for BOG Lunch and Learn Series, "What We Do"

## 1.5 WPs
Office of the Inspector General and Director of Compliance (OIGC)
July 1, 2008 – June 30, 2009
DETAILED WORK PLAN
PRIMARY ACTIVITY | LEGAL AUTHORITY | ACTIONS TAKEN OR PLANNED | STAFF | STATUS | COMPLETION DATE | DELIVERABLE | ACTIONS ITEMS/PLAN PROCESS | PLAN IMPLEMENTATION PROCESS | ESTIMATED HOURS
1.0 Establishment of OIGC
1.5 Prepare Summary Work Plan (SWP) and Detailed Work Plan (DWP)
|  | Action Taken: • Draft SWP for Chancellor's feedback and review. • Obtain input from Audit Chair and Vice Chair. Planned: • Present SWP to Audit Committee and Chancellor for feedback. | Harper/Clark | Draft complete and awaiting approval | SWP submitted to the BOG and Chancellor DWP completed for each activity | October, 2008

## 1.6 Doc Mgmt Sys
Office of the Inspector General and Director of Compliance (OIGC)
July 1, 2008 – June 30, 2009
DETAILED WORK PLAN
PRIMARY ACTIVITY | LEGAL AUTHORITY | ACTIONS TAKEN OR PLANNED | STAFF | STATUS | COMPLETION DATE | DELIVERABLE | ACTIONS ITEMS/PLAN PROCESS | PLAN IMPLEMENTATION PROCESS | ESTIMATED HOURS
1.0 Establishment of OIGC
1.6 Develop Document Management Index System
|  | Action Taken: • Contacted Information Resource Management staff for assistance in identifying software solutions. Planned: • Contact OIG/SUS offices for additional index examples or software application recommendations | Clark/Harper | Pending | Database for tracking and reporting of investigative and audit cases | January, 2009

## 1.7 Web
Office of the Inspector General and Director of Compliance (OIGC)
July 1, 2008 – June 30, 2009
DETAILED WORK PLAN
PRIMARY ACTIVITY | LEGAL AUTHORITY | ACTIONS TAKEN OR PLANNED | STAFF | STATUS | COMPLETION DATE | DELIVERABLE | ACTIONS ITEMS/PLAN PROCESS | PLAN IMPLEMENTATION PROCESS | ESTIMATED HOURS
1.0 Establishment of OIGC
1.7 Develop OIGC Web Presence
|  | Action Taken: • Identified components to be posted to OIGC web page. Planned: • Create materials to include on Web page • When materials are ready, send to Web Manager • Obtain input from senior staff | Clark/Harper | Pending | Comprehensive and Helpful Web site | March, 2009

## 2.1 BOG Audit WP
Office of the Inspector General and Director of Compliance (OIGC)
July 1, 2008 – June 30, 2009
DETAILED WORK PLAN
PRIMARY ACTIVITY | LEGAL AUTHORITY | ACTIONS TAKEN OR PLANNED | STAFF | STATUS | COMPLETION DATE | DELIVERABLE | ACTIONS ITEMS/PLAN PROCESS | PLAN IMPLEMENTATION PROCESS | ESTIMATED HOURS
2.0 Legal and Statutory Requirements
2.1 Implementation of BOG Office Audit Work Plan
| BOG F.S. 20.055 | Actions Taken: •Developed "Risk Assessment Questionnaire" to gather general operational data •Reviewed other agency Risk Assessment processes •Reviewed Professional Standards to conducting assessment and developing Audit Plan. Planned: •Distribution of Risk Assessment Questionnaire and schedule meetings with key staff •Follow-up meetings with BOG members and Chancellor •Analyze data to determine areas of highest risk •Submit draft Audit Plan to Audit Committee for discussion and approval. | Harper/Clark | Pending |  | Audit Plan for Committee's approval. |  |  | 100

## 2.2 AR
Office of the Inspector General and Director of Compliance (OIGC)
July 1, 2008 – June 30, 2009
DETAILED WORK PLAN
PRIMARY ACTIVITY | LEGAL AUTHORITY | ACTIONS TAKEN OR PLANNED | STAFF | STATUS | COMPLETION DATE | DELIVERABLE | ACTIONS ITEMS/PLAN PROCESS | PLAN IMPLEMENTATION PROCESS | ESTIMATED HOURS
2.0 Legal and Statutory Requirements
2.2 BOG OIGC Annual Report
| BOG F.S. 20.055 | Action Taken: • Components of Annual Report identified to be included Planned: • Draft sections on Audit Activities and Investigative Activities • Draft to be vetted with key constituents | Harper/Clark | Completed for FY 2008 | Due annually September 30th | Annual Report submitted to designated entities

## 2.3 AG
Office of the Inspector General and Director of Compliance (OIGC)
July 1, 2008 – June 30, 2009
DETAILED WORK PLAN
PRIMARY ACTIVITY | LEGAL AUTHORITY | ACTIONS TAKEN OR PLANNED | STAFF | STATUS | COMPLETION DATE | DELIVERABLE | ACTIONS ITEMS/PLAN PROCESS | PLAN IMPLEMENTATION PROCESS | ESTIMATED HOURS
2.0 Legal and Statutory Requirements
2.3 Respond to Auditor General Operational Audit and Six-month Follow-up
| BOG F.S. 20.055 | Action Taken: • Met with auditor manager and lead auditors • Established communication protocol for all SUS audits to be transmitted to OIGC Planned: • Develop agenda • Schedule meeting with Auditor General and Chancellor | Harper/Clark | Pending | 2009-12-01 | Letter agreement with Auditor General

## 3.1 CAEs
Office of the Inspector General and Director of Compliance (OIGC)
July 1, 2008 – June 30, 2009
DETAILED WORK PLAN
PRIMARY ACTIVITY | LEGAL AUTHORITY | ACTIONS TAKEN OR PLANNED | STAFF | STATUS | COMPLETION DATE | DELIVERABLE | ACTIONS ITEMS/PLAN PROCESS | PLAN IMPLEMENTATION PROCESS | ESTIMATED HOURS
3.0 Liaison Activities
3.1 Meetings with SUS Chief Audit Executive and Audit Committee Chairs
| BOG F.S. 20.055 | Action Taken: • Submitted draft Charter for comment • Reviewed response from SUAC Planned: • Schedule meeting with SUS Chief Audit Executives • Develop agenda for SUAC meetings | Harper/Clark | Pending | 2009-02-01 | Communication protocol

## 3.2 BOG AACC Mtgs
Office of the Inspector General and Director of Compliance (OIGC)
July 1, 2008 – June 30, 2009
DETAILED WORK PLAN
PRIMARY ACTIVITY | LEGAL AUTHORITY | ACTIONS TAKEN OR PLANNED | STAFF | STATUS | COMPLETION DATE | DELIVERABLE | ACTIONS ITEMS/PLAN PROCESS | PLAN IMPLEMENTATION PROCESS | ESTIMATED HOURS
3.0 Liaison Activities
3.2 Plan and Schedule BOG Audit Committee Meetings
| BOG F.S. 20.055 | Planned: • Prepare status of activities and work plans • Submit report on BOG Operational Audit | Harper/Clark | Pending | 2008-09-24

## 3.3 AG Mtg
Office of the Inspector General and Director of Compliance (OIGC)
July 1, 2008 – June 30, 2009
DETAILED WORK PLAN
PRIMARY ACTIVITY | LEGAL AUTHORITY | ACTIONS TAKEN OR PLANNED | STAFF | STATUS | COMPLETION DATE | DELIVERABLE | ACTIONS ITEMS/PLAN PROCESS | PLAN IMPLEMENTATION PROCESS | ESTIMATED HOURS
3.0 Liaison Activities
3.3 Schedule Meeting with Auditor General
| BOG F.S. 20.055 | Action Taken: • Met with auditor manager and lead auditors • Established communication protocol for all SUS audits to be transmitted to OIGC Planned: • Develop agenda • Schedule meeting with Auditor General and Chancellor | Harper/Clark | Pending | 2009-12-01 | Letter agreement with Auditor General

## 3.4 Leg
Office of the Inspector General and Director of Compliance (OIGC)
July 1, 2008 – June 30, 2009
DETAILED WORK PLAN
PRIMARY ACTIVITY | LEGAL AUTHORITY | ACTIONS TAKEN OR PLANNED | STAFF | STATUS | COMPLETION DATE | DELIVERABLE | ACTIONS ITEMS/PLAN PROCESS | PLAN IMPLEMENTATION PROCESS | ESTIMATED HOURS
3.0 Liaison Activities
3.4 Coordinate Legislative Briefings
| BOG F.S. 20.055 | Planned: • Meet with BOG, Chancellor, and Legislative Affairs Director • Schedule briefing with Joint Legislative Auditing Committee staff | Harper/Clark | Pending | 2009-02-01 | Meeting schedule

## 3.5 Law Enf
Office of the Inspector General and Director of Compliance (OIGC)
July 1, 2008 – June 30, 2009
DETAILED WORK PLAN
PRIMARY ACTIVITY | LEGAL AUTHORITY | ACTIONS TAKEN OR PLANNED | STAFF | STATUS | COMPLETION DATE | DELIVERABLE | ACTIONS ITEMS/PLAN PROCESS | PLAN IMPLEMENTATION PROCESS | ESTIMATED HOURS
3.0 Liaison Activities
3.5 Liaison with Law Enforcement Officials
| BOG F.S. 20.055 | Action Taken: • Met with FDLE and two SUS police chiefs Planned: •Identify contacts with FDLE and SUS police chiefs | Harper | Pending | 2009-02-01 | Protocol for Communication and Information

## 4.1 FAMU TF
Office of the Inspector General and Director of Compliance (OIGC)
July 1, 2008 – June 30, 2009
DETAILED WORK PLAN
PRIMARY ACTIVITY | LEGAL AUTHORITY | ACTIONS TAKEN OR PLANNED | STAFF | STATUS | COMPLETION DATE | DELIVERABLE | ACTIONS ITEMS/PLAN PROCESS | PLAN IMPLEMENTATION PROCESS | ESTIMATED HOURS
3.0 Liaison Activities
4.1 FAMU Task Force Project: Follow-up on Recommendations
|  | Action Taken: • Follow-up tasks identified. Planned: • Review/validate UBOT Task Force Recommendations • Verify FAMU UBOT action on Task Force • Review distribution - confirm receipt • Schedule meetings with key Legislative members and staff • Schedule meetings with Auditor General • Schedule meeting with FAMU President | Harper/Clark | Pending | 2009-01-01 | Follow-up Report to Audit Committee and BOG