## Sheet1
BOARD OF GOVERNORS Student Affairs Committee SUS Council for Student Affairs 2009-10 Work Plan: EXCESSIVE ALCOHOL USE
Goal: To Implement a Coordinated, System-Wide Initiative to Reduce Excessive Drinking by SUS Students
Issue | Lead Person(s) Responsible | Supporting Participants | Actions/Deliverables | Target Dates | Comments/Updates
I. Raise Awareness of Alcohol Abuse Issues | • Ann Duncan, BOG Student Affairs Committee • Maribeth Ehasz | • Council for Student Affairs, • Florida Alliance* | • BOG Committee meeting(s). • Prioritize & gain commitment. • Marketing. | • 6/18/09 • Fall 2009 • 2009-10 | • Will promote a culture of legal and responsible drinking with a focus on student health. • Will be an ongoing initiative.
II. Current Statistics and Research | • Patricia Telles-Irvin | • Maureen Miller and Florida Alliance | • Collect and disseminate information on alcohol use, abuse, & prevention. | Fall 2009 | • Will update existing knowledge of the issues and identify targets for response.
III. SUS Campus Programs and Services on Alcohol Use, Prevention, Intervention. | • Patricia Telles-Irvin • Jon Rogers | • Maureen Miller, Tom Hall and Florida Alliance | • A one-page chart of existing SUS programs. • A comprehensive SUS survey. | - For 9/24 SAC - Fall 2009 | • Will verify the proactive and extensive programming currently in place in the SUS. • Will share and promote Best Practices in the SUS.
IV. Florida Law and Local Ordinances | • Patricia Telles-Irvin | • Florida Alliance • University Lobbyists • Legislators | • Draft and propose legislation on: • Keg Registration. • Drink Specials. | Fall 2009 | • Will prepare for 2010 Legislature. • Will seek active support from BOG.
V. SUS Campus-Community Coalitions | • Maribeth Ehasz | Florida Alliance | • Identify effective coalitions using DCF and FDC Standards. • Promote components of effective coalitions. | Fall 2009 | • Will share and promote Best Practices in the SUS.
* Florida Higher Education Alliance for Substance Abuse Prevention