## Sheet1
STATE UNIVERSITY SYSTEM
FIXED CAPITAL OUTLAY LEGISLATIVE BUDGET REQUEST
CALENDAR
Department of
Education
| Universities/ | Commissioner/ | Board of
| Board of Trustees | Chancellor | Governors | Governor | Legislature
1
March |  | Draft Proposed General
Guidelines for Development
of SUS Legislative Budget
Request
2
April |  |  | Adopt General
Guidelines for
Development of SUS
Legislative Budget
Request
3
May |  | Draft Technical Instructions
for Submission of
University Five-Year Capital
Improvement Plan
4
June |  | Technical Instructions for
Submission of University
Five-Year Capital Improvement
Plans Prepared and
Distributed
| 6 | 5
July | Approve University Five- | Provide PECO Allocation
| Year Capital Improvement | Based on Latest Revenue
| Plan | Estimate
| 7 | 8
August | Submit University Five- | Prepare Chancellor's
| Year Capital Improvement | Recommended SUS Fixed
| Plan | Capital Outlay Legislative
Budget Request
|  | 10 | 9
September |  | Submit Approved SUS | Approve SUS Fixed
|  | Fixed Capital Outlay | Capital Outlay
|  | Legislative Budget Request | Legislative Budget
Request
11
October- |  |  |  | Development of
December |  |  |  | Governor's
Recommended
Budget
| 12 | 13 | 14 | 15
January | Submit Updated SUS | As needed, prepare | As needed, Approve | Governor's
| Facility Enhancement | Chancellor's Recommended | Amended SUS Fixed | Recommended
| Challenge Grant Program | Amended SUS Fixed Capital | Capital Outlay | Budget Released
| Information | Outlay Legislative Budget | Legislative Budget
|  | Request | Request
February
|  | 16 | 17 |  | 18
March |  | As needed, prepare | As needed, Approve |  | Legislature in
|  | Chancellor's Recommended | Amended SUS Fixed |  | Session
|  | Amended SUS Fixed Capital | Capital Outlay
|  | Legislative Budget Request | Legislative Budget
Request
18
April |  |  |  |  | Legislature in Session
19
May |  |  |  |  | General Appropriations
Bill Passed
20
June |  |  |  | General
Appropriations
Act Signed Into Law
*Order of activities shown by numbers