## Activities, Priorities, & Done
Office of the Inspector General and Director of Compliance (OIGC) Summary Work Plan Primary Activities, Top Priorities, and Completed Items July 1, 2008 - June 30, 2009
Primary Activities: 1.0 Establishment of OIGC 2.0 Legal and Statutory Requirements 3.0 Liaison Activities 4.0 Special Projects 5.0 Investigations | Top Priorities: • 1.1 Develop BOG Audit & Compliance Committee and OIGC Charters • 1.2 Develop Compliance Program Plan • 1.4 Develop Procedures for Monitoring University Audit & Compliance Activities • 1.5 Prepare Committee Work Plan, OIGC Summary Work Plan, and OIGC Detailed Work Plan • 2.1 Develop BOG Office Audit Work Plan • 4.1 FAMU Task Force Project Follow-up on Recommendations • 5.1 Establish Procedures and Forms (for Investigations) | Completed Items: • 1.1 Audit and Compliance Committee Charter created and approved by Committee (January 28, 2009) and BOG (March 29, 2009) • 1.5 Committee Work Plan developed and approved (January 28, 2009), Summary Work Plan approved by Committee (November 5, 2008) • 1.6 Document Management Index System created (January 2009) • 2.2 BOG OIGC 2008 Annual Report (September 30, 2008) • 2.3 Respond to Auditor General Audit, BOG Op Audit for FYE 2007 (September 26, 2008) • 4.1 FAMU Task Force Project Follow-up on Recommendations - reported to Board and announced BOG's role in project is concluded (January 29, 2009)

## Activities
Office of the Inspector General and Director of Compliance (OIGC) Summary Work Plan Activities July 1, 2008 - June 30, 2009
PRIMARY ACTIVITY | PRIORITY | LEGAL AUTHORITY | ACTIONS TAKEN/PLANNED | STAFF | DELIVERABLE | STATUS | COMPLETION DATE
1.0 Establishment of OIGC
1.1 Develop Audit & Compliance Committee (AACC) and OIGC Charters
| A | BOG F.S. 20.055 & 20.155 | Action Taken: • Draft Charter reviewed by Audit Committee and SUAC members. • Met with key constituencies; i.e., UBOT Audit Committee Chairs, individual Chief Audit Executive. • AACC and OIGC Charters separated and approved by Committee and Board at different times. Planned: •AACC Charter implementation document (procedures) •Post AACC Charter on IG Web page. | Harper/Clark | • AACC Charter • OIGC Charter | •COMPLETED • Pending | • March, 2009 • June, 2009
1.2 Develop Compliance Program Plan
| A | BOG F.S. 20.055 & 20.155 | Action Taken: • Reviewed SUS and peer institutions compliance programs; identified three institutions (USF, FAMU, and FIU) Compliance Officers; reviewed/identified National Professional Associations in compliance area. Planned: • Face-to-face or conference call meetings with SUS compliance officers • Meet with other university system compliance executives (University of Texas, North Carolina, and Georgia). • Planning meeting to develop a risk assessment/compliance project. | Harper/Clark | A published compliance structure and training materials | Pending | January, 2010
1.3 Develop OIGC Policies & Procedures
For: Handling Consumer Complaints | B |  | Action Taken: • Met with appropriate BOG staff to discuss needs and current procedures for tracking and handling consumer complaints and investigation requests. Planned: • Draft Audit/Investigative procedures for OIGC and obtain input from SUS member institutions. • Establishment of policies and procedures for OIGC unit and BOG How To Manual. | Harper/Clark | Submission of policies and procedures to BOG and Chancellor | Pending | December, 2009
For: Communication protocol with Audit and Compliance Committee on investigations, SUS audit reports, and BOG audit reports. | B | Audit and Compliance Committee Charter BOG Reg. 1.001 | Action Taken: • Functional analysis draft in progress to list IG actions needed to comply with AACC Charter as well as the new BOG Regulation (1.001) for UBOT Powers and Duties Planned: • Establish reporting process for Inspector General to inform Audit and Compliance Committee (AACC) of results of preliminary investigation(s) into any audit, compliance, or grievance matter where it appears a university and/or its Board of Trustees is unwilling or unable to provide for objective investigation. • Establishment of policies and procedures for OIGC unit and BOG How To Manual. | Harper/Clark | Submission of policies and procedures to BOG and Chancellor | Pending | July, 2009
For: Responses to AG audits of BOG office (see 2.3) | B |  | Action Taken: • Internal procedures for communication with AG's office held with appropriate BOG senior staff. IG's role defined. Planned: • Establishment of policies and procedures for OIGC unit and BOG How To Manual. | Harper | Submission of policies and procedures to BOG and Chancellor | Pending | July, 2009
For: Receipt and processing of university audit reports (including internal audits) | B | Audit and Compliance Committee Charter BOG Reg. 1.001 | Action Taken: • Dissemination of AACC Charter to SUS with follow-up conference calls to discuss best procedures | Harper/Clark | Submission of policies and procedures to BOG and Chancellor | Pending | July, 2009
1.4 Develop Procedures for Monitoring University Audit & Compliance Activities
| A |  | Action Taken: • Reviewed previous data request procedures • Obtained sample scope of work from outside vendor to develop a "checklist" model. Planned: • Identify peer systems that have developed oversight framework. • Obtain input from individual SUS institutions. • Convene a meeting of representatives from SUS members to discuss a value-added approach. | Harper/Clark | Procedures and manual for monitoring SUS audits and investigation reports | Pending | January, 2010
1.5 Prepare Committee Work Plan (CWP), OIGC Summary Work Plan (SWP), and OIGC Detailed Work Plan (DWP)
| A |  | Action Taken: • CWP and SWP approved by Committee January 28, 2009. Planned: • SWP and DWP will be dynamic documents with revisions made as appropriate. | Harper/Clark | • CWP for Committee use and BOG meeting planning • SWP and DWP for OIGC use | • CWP COMPLETED • SWP COMPLETED • DWP in progress | • January, 2009 (CWP) • November, 2008 (SWP) • December, 2010 (DWP)
1.6 Develop Document Management Index System
| B |  | Action Taken: • Contacted Information Resource Management staff for assistance in identifying software solutions. • Contacted OIG/SUS offices for additional index examples or software application recommendations. • Access data base created to index and track all matters, complaints, and investigations. | Clark/ Harper | Database for tracking and reporting of investigative and audit cases | COMPLETED | January, 2009
1.7 Develop OIGC Web Presence
| C |  | Action Taken: • Identified components to be posted to OIGC web page. Planned: • Create materials to include on Web page • When materials are ready, send to Web Manager • Obtain input from senior staff | Harper/Clark | Comprehensive and Helpful Web site | Pending | August, 2009
2.0 Legal and Statutory Requirements
2.1 Implementation of BOG Office Audit Work Plan
| A | BOG F.S. 20.055 | Actions Taken: • Developed "Risk Assessment Questionnaire" to gather general operational data • Reviewed other agency Risk Assessment processes • Reviewed Professional Standards to conducting assessment and developing Audit Plan. Planned: • Distribution of Risk Assessment Questionnaire and schedule meetings with key staff • Follow-up meetings with BOG members and Chancellor • Analyze data to determine areas of highest risk • Submit draft Audit Plan to Audit Committee for discussion and approval. | Harper/Clark | Audit Plan | Pending | December, 2009
2.2 BOG OIGC Annual Report
2008 | A | BOG F.S. 20.055 | Action Taken: • Components of Annual Report identified to be included Planned: • Draft sections on Audit Activities and Investigative Activities • Draft to be vetted with key constituents | Harper/Clark | Annual Report submitted to designated entities | COMPLETED | 2008-09-30
2009 | D | BOG F.S. 20.055 | Action Taken: • The 2008 Annual Report will serve as a template for the 2009 report. Additionally, reports from other agencies have been reviewed for features to consider in the 2009 report. Planned: • IG and staff will meet in May 2009 to begin discussion on the 2009 report's format and content. | Harper/Clark | Annual Report to be submitted to designated entities and posted on the BOG IG Web site. | Pending | 2009-09-30
2.3 Respond to Auditor General Audits of BOG Office
2007 Op Audit (with some activities from 2008) | C |  | Action Taken: • Met with key BOG staff to review FY 6/30/07 preliminary report and create action plan (CAP) for response and corrections • Scheduled six-month follow-up to assess effectiveness of corrective actions. Planned: •Submit summary of BOG staff CAPs to BOG and AG's office. | Harper/Clark and other BOG staff | • BOG response completed. •Six-month follow-up report for Corrective Action Plan | COMPLETED | • September 26, 2009 for BOG report. • June, 2009 for six-month follow-up.
2009 Op Audit | C |  | Action Taken: • 2009 Op Audit delayed by AG's office until May or June, 2009. | Harper/Clark and other BOG staff | •Audit Plan •Response to any P&T findings •Formal response to final report | Pending
3.0 Liaison Activities
3.1 Meetings with SUS Chief Audit Executive and Audit Committee Chairs
| C | BOG F.S. 20.055 | Action Taken: • Submitted draft Charter for comment • Reviewed response from SUAC • Met with SUAC 11/19/08. Planned: • Schedule meeting with SUS Chief Audit Executives for conference call and eventual face-to-face meeting • Develop agenda for SUAC meetings | Harper/Clark | Communication protocol | Pending | July, 2009
3.2 Plan and Schedule BOG Audit Committee Meetings
| C | BOG F.S. 20.055 | Action Taken: • AACC meeting schedule approved for FY 2008-2009. AACC members assigned as leads for action items on Committee Work Plan (approved January 28, 2009). Planned: • Prepare status of activities and work plans • Submit report on BOG Operational Audit | Harper/Clark | Agenda and meeting materials as needed. | Pending | n/a
3.3 Schedule Meeting with the Auditor General
| D | BOG F.S. 20.055 | Action Taken: • Met with auditor manager and lead auditors • Established communication protocol for all SUS audits to be transmitted to OIGC Planned: • Develop agenda • Schedule meeting with Auditor General and Chancellor | Harper/Clark | Letter agreement with Auditor General | Pending | December, 2009
3.4 Coordinate Legislative Briefings
| D | BOG F.S. 20.055 | Planned: • Meet with BOG, President in Residence, and Legislative Affairs Director • Schedule briefing with Joint Legislative Auditing Committee staff • Responded to several Legislative staff requests for information. | Harper/Clark |  | As needed
3.5 Liaison with Law Enforcement Officials
| D | BOG F.S. 20.055 | Action Taken: • Met with FDLE and two SUS police chiefs Planned: •Identify contacts with FDLE and SUS police chiefs | Harper | Protocol for Communication and Information | As needed
3.6 Schedule and Plan UBOT Audit Committee Workshop (Annually, in August)
| D |  | Action Taken: • BOG AACC Chair Tripp not available for Work Shop in August 2009. Planned: • Identify any new UBOT audit committee members who should attend. | Harper/Clark | Agenda and meeting materials as needed. | Pending | TBD
4.0 Special Projects
4.1 FAMU Task Force Project Follow-up on Recommendations
| A |  | Action Taken: • Follow-up tasks identified. • Reviewed/validated UBOT Task Force Recommendations • Verified FAMU UBOT action on Task Force • Scheduled meetings with key Legislative members and staff • Scheduled meetings with Auditor General • Scheduled meeting with FAMU President • FAMU President presented follow-up report to Audit and Compliance Committee | Harper/Clark | Follow-up Report to Audit Committee and BOG | COMPLETED | January, 2009
5.0 Investigations
5.1 Establish Procedures and Forms for Investigations
| A | Audit and Compliance Committee and Office of the Inspector General and Director of Compliance Charters | Action Taken: • Procedures under development in response to investigations (or requests for) from internal BOG staff or directly from complainant. Planned: • Establishment of report format to use in closing investigations and reporting to appropriate entities the outcome. | Harper/Clark | Report at close investigation | As needed