| Board of Governors – State University System of Florida Audit and Compliance Committee Work Plan |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| BOG Lead: Norman Tripp Lead Staff: Derry Harper/Lori Clark Additional BOG Members: John Dasburg, Charles Edwards, Frank Martin, Office of the Inspector General and Tico Perez, Gus Stavros, John Temple, and Zach Zachariah Director of Compliance (OIGC) |  |  |  |  |  |  |
| Goals and Deliverables: - Approve Charters for the Audit and Compliance Committee (AACC) and the Office of the Inspector General and Director of Compliance - Develop and Approve BOG Office and SUS Compliance Program - Approve Office of the Inspector General and Director of Compliance (OIGC) Policies and Procedures - Approve OIGC Work Plan - Adopt Procedures for Monitoring University Audit and Compliance Activities - Approve BOG Office Internal Audit Work Plan - Accept OIGC Annual Report - Annual Review of AACC and OIGC Charters |  |  |  |  |  |  |
| I. Audit and Compliance Committee and OIGC Charters |  |  |  |  |  |  |
| Actions/Deliverables | Lead Person(s) Responsible | Start Date |  | End Date |  | Comments |
|  |  | Planned | Actual | Planned | Actual |  |
| I.A. AACC: Discuss current Charter drafts | Tripp | 11/5/08 | 11/5/08 | 11/5/08 | 1/28/09 |  |
| I.B. AACC: Review final Charters for recommendation to full Board | Tripp | 1/29/09 | 1/28/09 | 1/29/09 | 1/28/09 | Revision process will be handled by email or conference call. 11/19/08 – Derry Harper met with SUS State University Audit Council members to discuss Charter drafts. The AACC met 1/28/09 and discussed comments and suggestions by all interested parties. The OIGC Charter will be revised and submitted for review and approval once the AACC Charter is approved by the Board. The AACC Charter was approved by the Committee on 1/28/09. The OIGC Charter will be reviewed and approved after the process is completed for the Audit and Compliance Committee Charter. |
| I.C. Board: Approval of AACC Charter | Tripp | 3/26/09 | 3/26/09 | 3/26/09 | 3/26/09 |  |
| I.D. AACC: Review final OIGC Charter for recommendation to full Board | Tripp | 11/5/08 | 5/19/09 | 6/18/09 | 5/19/09 |  |
| I.E. Board: Approval of OIGC Charter | Tripp | 8/6/09 | 6/18/09 | 8/6/09 | 6/18/09 |  |
| II. SUS Compliance Program Plan |  |  |  |  |  |  |
| Actions/Deliverables | Lead Person(s) Responsible | Start Date |  | End Date |  | Comments |
|  |  | Planned | Actual | Planned | Actual |  |
| II.A. AACC: Discuss proposed SUS Compliance Program Plan | Temple | 6/16-17/10 |  | 6/16-17/10 |  | Report from work group on the results of their research of current trends in compliance area. |
| II.B. AACC: Adopt SUS Compliance Program Plan | Temple and Tripp | 9/15-16/10 |  | 9/15-16/10 |  |  |

| III. OIGC Policies and Procedures |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Actions/Deliverables | Lead Person(s) Responsible | Start Date |  | End Date |  | Comments |
|  |  | Planned | Actual | Planned | Actual |  |
| III.A. AACC: Discuss proposed OIGC Policies & Procedures | Stavros | 6/16-17/10 |  | 6/16-17/10 |  | Determine when OIGC will be the subject of Auditor General Quality Assurance Review. |
| III.B. AACC: Approve OIGC Policies & Procedures | Stavros and Tripp | 9/15-16/10 |  | 9/15-16/10 |  |  |
| IV. Audit and Compliance Committee Work Plan |  |  |  |  |  |  |
| Actions/Deliverables | Lead Person(s) Responsible | Start Date |  | End Date |  | Comments |
|  |  | Planned | Actual | Planned | Actual |  |
| IV.A.1. AACC: Discuss proposed OIGC work plan | Tripp | 11/5/08 | 11/5/08 | 11/5/08 | 11/5/08 | Committee discussed OIGC and AACC Summary Work Plan. The Committee will now need to review this document and provide guidance and prioritization. |
| IV.A.2. AACC: Review 2009-2010 OIGC Summary Work Plan | Tripp | 1/28/10 |  | 1/28/10 |  | Annual review of work plan. |
| IV.B.1. AACC: Adopt AACC work plan | Tripp | 1/29/09 | 1/28/09 | 1/29/09 | 1/28/09 | 1/28/09 – The AACC adopted the Committee Work Plan. |
| IV.B.2. AACC: Adopt revised AACC work plan | Tripp | 1/28/10 |  | 1/28/10 |  | Annual review of work plan. |

| V. Monitoring University Audit and Compliance Activities |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Actions/Deliverables | Lead Person(s) Responsible | Start Date |  | End Date |  | Comments |
|  |  | Planned | Actual | Planned | Actual |  |
| V.A. AACC: Discuss Committee’s role in monitoring university audit and compliance activities | Edwards | 11/5/08 | 11/5/08 | 11/5/08 | 11/5/08 | This is part of the discussion of the AACC Charter draft. The completion date for this item will coincide with that of the Charter approval. |
| V.B. AACC: Review proposed procedures for appropriately monitoring university reports | Edwards and Tripp | 1/28/10 |  | 1/28/10 |  | Procedures will be developed and coordinated with SUS members of the Compliance Work Group. |
| VI. BOG Office Audit Work Plan |  |  |  |  |  |  |
| Actions/Deliverables | Lead Person(s) Responsible | Start Date |  | End Date |  | Comments |
|  |  | Planned | Actual | Planned | Actual |  |
| VI.A. AACC: Discuss draft of Risk-based Audit Work Plan of BOG Office | Zachariah | 11/5/08 |  | 6/16-17/10 |  | Committee will receive status report on BOG Office Risk Assessment process. |
| VI.B. Board: Approve Audit Work Plan of BOG Office for staff implementation. | Tripp | 6/16-17/10 |  | 9/15-16/10 |  | Committee will review and adopt 2009 Audit Work Plan. |
| VII. OIGC Annual Report |  |  |  |  |  |  |
| Actions/Deliverables | Lead Person(s) Responsible | Start Date |  | End Date |  | Comments |
|  |  | Planned | Actual | Planned | Actual |  |
| VII.A. AACC: Approved FY 2008 Annual Report for OIGC | Tripp | 10/1/08 | 10/1/08 | 11/5/08 | 11/5/08 | Submitted to Board Chair and Chancellor on 9/30/08. Approved by AACC 11/5/08. |
| VII.B. AACC: Approve FY 2009 Annual Report for OIGC | Tripp | 1/28/10 |  | 1/28/10 |  | Due annually by September 30th to Board Chair and Chancellor |

| VIII. Response to Auditor General Operational Audit and Six-Month Follow-up |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Actions/Deliverables | Lead Person(s) Responsible | Start Date |  | End Date |  | Comments |
|  |  | Planned | Actual | Planned | Actual |  |
| VIII.A. AACC: Review BOG response to 2008 Operational Audit by Florida Auditor General’s Office | Martin | 10/8/08 | 10/8/08 | 11/5/08 | 11/5/08 | Final report released by AG’s office on October 8, 2008 |
| VIII.B. AACC: Review six-month follow-up response to Auditor General Operational Audit | Martin and Tripp | 6/18/09 | 5/19/09 | 6/18/09 | 5/19/09 | BOG Chair and audit committee chair notified by email of status. (No. 2009-019) |

| IX. Annual Review of AACC and OIGC Charters |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Actions/Deliverables | Lead Person(s) Responsible | Start Date |  | End Date |  | Comments |
|  |  | Planned | Actual | Planned | Actual |  |
| IX.A. AACC: Discuss Committee and OIGC Charters | Tripp | 1/28/10 |  | 3/17-18/10 |  | Charters approved by Committee and full board in 2010. Discussion will be held in one year for any changes needed. |
| IX.B. AACC: Approve Committee and OIGC Charters | Tripp | 3/17-18/10 |  | 3/17-18/10 |  |  |
| X. FAMU Task Force Project: Follow-up on Recommendations |  |  |  |  |  |  |
| Actions/Deliverables | Lead Person(s) Responsible | Start Date |  | End Date |  | Comments |
|  |  | Planned | Actual | Planned | Actual |  |
| X.A. Board: Report from FAMU President on status of Corrective Action Plan and update on status of Task Force Recommendations | Tripp | 1/29/09 | 1/28/09 | 1/29/09 | 1/28/09 | President Ammons reported that the remaining Corrective Action Plans have been implemented. The Board concluded its work on this project. |