## Activities
Office of the Inspector General and Director of Compliance (OIGC) Summary Work Plan July 1, 2009 - June 30, 2010
Primary Activities: 1.0 Establishment of OIGC 2.0 Legal and Statutory Requirements 3.0 Liaison Activities 4.0 Special Projects 5.0 Investigations |  | Top Priorities: • 1.2 Develop Compliance Program • 1.4 Develop Procedure for Monitoring Audit & Compliance Activities • 2.1 Develop BOG Office Audit Work Plan • 2.2 Prepare BOG OIGC 2009 Annual Report • 5.1 Establish Procedures and Forms (for Investigations) |  | Completed Items: • 2.2 BOG OIGC 2009 Annual Report submitted 9/30/09.
PRIMARY ACTIVITY | PRIORITY | LEGAL AUTHORITY | ACTIONS TAKEN/PLANNED | STAFF | DELIVERABLE | STATUS | COMPLETION DATE
1.0 Establishment of OIGC
1.1 Annual Review of Audit & Compliance Committee (AACC) and OIGC Charters
|  | BOG F.S. 20.055 & 20.155 | Planned: • Review Charters for necessary updates or general revisions. • Meet/confer with key constituencies (UBOT Audit Committee Chairs, Chief Audit Executives, etc.) • Present to Committee and then full Board in the spring for review and approval. • Post both Charters on IG Web page. | Harper/Clark | • AACC Charter • OIGC Charter | Pending | March, 2010
1.2 Develop Compliance Program
1.2.a. Create BOG/SUS Compliance Infrastructure consistent with AACC Charter. | A | BOG F.S. 20.055 & 20.155 | Action Taken: • Reviewed SUS and peer institutions compliance programs; identified three institutions (USF, FAMU, and FIU) Compliance Officers; reviewed/identified National Professional Associations in compliance area. • 8/11/09 - first conference call with group • Met with BOG Compliance Steering Committee • Planning meeting to develop a risk assessment/compliance project. • Developed database tool to review BOG Regulations for compliance and to create a compliance matrix. Planned: • Regular face-to-face or conference call meetings with SUS compliance officers • Meet with other university system compliance executives (University of Texas, North Carolina, and Georgia). | Harper/Clark | Recommend a compliance organization and structure | Pending | September, 2010
1.2.b. Develop OIGC Policies & Procedures for Monitoring SUS Compliance/ Audit Activities | A | BOG F.S. 20.055, 20.155, and BOG Reg. 1.001 | Action Taken: • Reviewed previous data request procedures • Obtained sample scope of work from outside vendor to develop a "checklist" model. • Identified areas of compliance: 1) Data Requests (Form 990s, DSO external audits, University internal audits), 2) AG Financial and Operational Audits, 3) OPPAGA reports, 4) BOG Operational Audits, 5) American Recovery and Reinvestment Act of 2009. Planned: • Identify peer systems that have developed oversight framework. • Obtain input from individual SUS institutions. • Convene Compliance Work Group (CWG), composed of SUS representatives, to discuss value-added approach to compliance. | Harper/Clark |  | Pending | January, 2010
1.3 Develop OIGC Policies & Procedures
1.3.a. Processing Consumer Complaints | B |  | Action Taken: • Met with appropriate BOG staff to discuss needs and current procedures for tracking and handling consumer complaints and investigation requests. • Draft Audit/Investigative procedures for OIGC and obtain input from SUS member institutions. | Harper/Clark | Submission of policies and procedures to BOG and Chancellor | Completed | March, 2009
1.3.b. Communication protocol with Audit and Compliance Committee on investigations, SUS audit reports, and BOG audit reports. | B | Audit and Compliance Committee Charter BOG Reg. 1.001 | Action Taken: • Functional analysis draft in progress to list IG actions needed to comply with AACC Charter as well as the new BOG Regulation (1.001) for UBOT Powers and Duties Planned: • Establish reporting process for Inspector General to inform Audit and Compliance Committee (AACC) of results of preliminary investigation(s) into any audit, compliance, or grievance matter where it appears a university and/or its Board of Trustees is unwilling or unable to provide for objective investigation. • Establishment of policies and procedures for OIGC unit and BOG How To Manual. | Harper/Clark | Submission of policies and procedures to BOG and Chancellor | Pending | September, 2010
1.3.c. Responses to AG audits of BOG office (see 2.3) | B |  | Action Taken: • Internal procedures for communication with AG's office held with appropriate BOG senior staff. IG's role defined. Planned: • Establishment of policies and procedures for OIGC unit and BOG How To Manual. | Harper | Submission of policies and procedures to BOG and Chancellor | Pending | September, 2010
1.3.d. Receipt and processing of university audit reports (including internal audits) | B | Audit and Compliance Committee Charter BOG Reg. 1.001 | Action Taken: • Dissemination of AACC Charter to SUS with follow-up conference calls to discuss best procedures. • 10/22/09 - Requested copy of SUS internal audit reports be sent to OIGC. • Draft data request ready to submit to SUS-Submissions to set up quarterly request for SUS internal audit reports. Planned: • Data request (SUS-Submissions) | Harper/Clark | Submission of policies and procedures to BOG and Chancellor | Pending | September, 2010
1.4 Semi-Annual Review of Committee Work Plan (CWP), OIGC Summary Work Plan (SWP), and OIGC Detailed Work Plan (DWP)
1.4.a. CWP |  |  | Action Taken: • CWP approved by Committee January 28, 2009. Subsequent revisions done as requested by Exec. Vice Chancellor. Planned: • Document revised by OIGC January, 2010. | Harper/Clark | CWP for Committee use and BOG meeting planning | On-going | n/a
1.4.b. SWP |  |  | Action Taken: • SWP will be dynamic documents with revisions made and submitted to Committee for review and approval as appropriate. | Harper/Clark | SWP for OIGC project planning, orientation, and training | On-going | n/a
1.4.c. DWP | C |  | Action Taken: • DWP drafted and revised frequently. Like the SWP, the DWP will be a dynamic document with revisions made as appropriate. | Harper/Clark | DWP for OIGC planning and project development | On-going | n/a
1.5 Develop OIGC Outreach and Training
1.5.a. Staff Orientation to IG Role | B |  | Action Taken: • Lunch and Learn Session Held 9/2/09 | Harper/Clark | Lunch & Learn session | Completed | September, 2009
1.5.b. AACC Handbook | B |  | Action Taken: • identified intended audience and uses (resource for AACC members, orientation for new AACC members, and orientation for new Chancellor). Planned: • Identify any new materials needed • Ask key staff to proof | Clark/ Harper | Comprehensive Handbook for multiple uses | On-going | n/a
1.5.c. Posting of OIGC Reports and Charters for Public Access | C |  | Action Taken: • Identified components to be posted to OIGC Web page. Planned: • Revise text to include Annual Reports and Charters on Web page • Obtain input from senior staff | Harper/Clark | Comprehensive and Helpful Web site | Pending | June, 2010
2.0 Legal and Statutory Requirements
2.1 Implementation of BOG Office Audit Work Plan
| A | F.S. 20.055 | Actions Taken: • Developed "Risk Assessment Questionnaire" to gather general operational data • Reviewed other agency Risk Assessment processes • Reviewed Professional Standards to conducting assessment and developing Audit Plan. Planned: • Distribution of Risk Assessment Questionnaire and schedule meetings with key staff • Follow-up meetings with BOG members and Chancellor • Analyze data to determine areas of highest risk • Submit draft Audit Plan to Audit Committee for discussion and approval. | Harper/Clark | Audit Plan | Pending | March, 2010
2.2 BOG OIGC Annual Report
2008-2009 | B | F.S. 20.055 | Action Taken: • The 2008 Annual Report served as a template for the 2009 report. Additionally, reports from other agencies have been reviewed for features to consider in the 2009 report. • IG and staff met in May 2009 to review components for 2008-2009 report. Planned: • Approved report will be filed in the IG Publish folder and will be posted on the IG Web page. | Harper/Clark | Annual Report to be submitted to designated entities and posted on the BOG IG Web site. | Completed | 2009-09-30
2.3 Respond to Auditor General Audits of BOG Office
2009 Op Audit | C |  | Action Taken: • 2009 Op Audit delayed by AG's office until May or June, 2009. | Harper/Clark and other BOG staff | •Audit Plan •Response to any P&T findings •Formal response to final report | Pending | TBD
3.0 Liaison Activities
3.1 Meetings with SUS Chief Audit Executive and Audit Committee Chairs
| C | BOG F.S. 20.055 | Action Taken: • AACC and OIGC Charters approved by AACC in 2009. • Met with SUS Chief Audit Executives October, 2009. • Established the "Brogan Doctrine" | Harper/Clark | Communication protocol | As needed | n/a
3.2 Plan and Schedule BOG Audit Committee Meetings
| C | BOG F.S. 20.055 | Action Taken: • AACC meeting schedule approved for FY 2008-2009. AACC members assigned as leads for action items on Committee Work Plan (approved January 28, 2009). Planned: • Prepare status of activities and work plans • Submit report on BOG Operational Audit • Review CWP and SWP with Committee | Harper/Clark | Agenda and meeting materials as needed. | Pending | n/a
3.3 Schedule Meeting with the Auditor General
| D | BOG F.S. 20.055 | Action Taken: • Met with auditor manager and lead auditors • Established communication protocol for all SUS audits to be transmitted to OIGC Planned: • Develop agenda • Schedule meeting with Auditor General and Chancellor, and State University Audit Council | Harper/Clark | Letter agreement with Auditor General | Pending | September, 2010
3.4 Coordinate Legislative Briefings
| D | BOG F.S. 20.055 | Planned: • Meet with BOG, Chancellor, and Legislative Affairs Director for guidance • Schedule briefing with Joint Legislative Auditing Committee staff | Harper/Clark |  | As needed
3.5 Schedule and Plan UBOT Audit Committee Workshop (Annually, in August)
| D |  | Action Taken: • No UBOT Workshop held in 2009. AACC Handbook created to use in orienting new Chancellor as well as BOG committee members. • New Chancellor orientation materials prepared that can also be used for UBOT workshop that might be scheduled at a different time of year. | Harper/Clark | Agenda and meeting materials as needed. | Pending | TBD
4.0 Special Projects
5.0 Investigations
5.1 Establish Procedures and Forms for Investigations
| A | Audit and Compliance Committee and Office of the Inspector General and Director of Compliance Charters | Action Taken: • Procedures under development in response to investigations (or requests for) from internal BOG staff or directly from complainant. • Responded and reviewed complaints submitted to BOG. Planned: • Establishment of report format to use in closing investigations and reporting to appropriate entities the outcome. | Harper/Clark | Final Report to close investigation | As needed | n/a